## Timesheet for Apr 01 - Apr 30,
Key | IssueType | Summary | User | Project | Status | IssueLoggerHours | BillableHours | StoryPoints | Clients | WorklogUsers | IssueEstimationHours | IssueRemainingHours | Fast Lane | More stories | AC Changes | Epic Status | Change type | Change risk | Change reason | AC Changes - secondary | Fast Lane - secondary
VC-1011 | Story | C/ Account: Account-tab, change account info | Angela Avetisyan | VEVA Collect | In Progress | 0.07 | 0.07 |  |  |  | 0 | 0
VC-975 | Bug | W/ Remove Jaxsta from My Party | Angela Avetisyan | VEVA Collect | Done | 0.03 | 0.03 | 1 |  |  | 0 | 0
VC-983 | Story | C/ Project: Expand credit row on session credit | Angela Avetisyan | VEVA Collect | In Progress | 0.2 | 0.2 |  |  |  | 0 | 0
VC-981 | Story | C/ Project: Edit credit for session | Angela Avetisyan | VEVA Collect | In Progress | 0.08 | 0.08 |  |  |  | 0 | 0
VC-1005 | Story | M/ F/NF/O logic | Angela Avetisyan | VEVA Collect | To Do | 0.2 | 0.2 | 3 |  |  | 0 | 0
VC-1015 | Story | C/ Account: Integrations-tab, check all about integration | Angela Avetisyan | VEVA Collect | In Progress | 0.17 | 0.17 |  |  |  | 0 | 0
VC-986 | Story | C/ Project: View a recording in a session | Angela Avetisyan | VEVA Collect | In Progress | 0.07 | 0.07 |  |  |  | 0 | 0
VC-985 | Story | C/ Project: Remove a recording from a session | Angela Avetisyan | VEVA Collect | In Progress | 0.17 | 0.17 | 1 |  |  | 0 | 0
VC-1012 | Story | C/ Account: Account-tab, change timezone | Angela Avetisyan | VEVA Collect | In Progress | 0.03 | 0.03 | 1 |  |  | 0 | 0
VC-1016 | Story | C/ Account: Integrations-tab, SoundExchange opt-in | Angela Avetisyan | VEVA Collect | To Do | 0.25 | 0.25 | 1 |  |  | 0 | 0
VC-953 | Story | C/ Song: Click to enter song details page | Angela Avetisyan | VEVA Collect | In Progress | 0.05 | 0.05 | 1 |  |  | 0 | 0
VC-997 | Story | W/ Modal if owner Locked a Project | Angela Avetisyan | VEVA Collect | Done | 0.08 | 0.08 |  |  |  | 0 | 0
VC-972 | Bug | W/ Fix positions on integration page | Angela Avetisyan | VEVA Collect | Done | 0.08 | 0.08 | 1 |  |  | 0 | 0 |  |  | 1
VC-978 | Story | C/ Project: Edit session details | Angela Avetisyan | VEVA Collect | In Progress | 0.08 | 0.08 |  |  |  | 0 | 0
VC-964 | Story | C/ Project: Expand/contract activity | Angela Avetisyan | VEVA Collect | To Do | 0.08 | 0.08 |  |  |  | 0 | 0
VC-966 | Story | C/ Project: Export RIN | Angela Avetisyan | VEVA Collect | To Do | 0.05 | 0.05 |  |  |  | 0 | 0
VC-967 | Story | C/ Project: Export PDF | Angela Avetisyan | VEVA Collect | To Do | 0.05 | 0.05 |  |  |  | 0 | 0
VC-958 | Story | C/ Project: Edit details | Angela Avetisyan | VEVA Collect | To Do | 0.08 | 0.08 |  |  |  | 0 | 0
VC-979 | Story | C/ Project: Assign recording to session | Angela Avetisyan | VEVA Collect | In Progress | 0.08 | 0.08 |  |  |  | 0 | 0
VC-833 | Story | M/ Type date manually | Angela Avetisyan | VEVA Collect | To Do | 0.25 | 0.25 | 2 |  |  | 0 | 0
VC-956 | Story | C/ Song: Search file | Angela Avetisyan | VEVA Collect | In Progress | 0.25 | 0.25 |  |  |  | 0 | 0.08
VC-952 | Story | C/ Songs: Change page in list | Angela Avetisyan | VEVA Collect | In Progress | 0.08 | 0.08 |  |  |  | 0 | 0
VC-980 | Story | C/ Project: Add credit to session | Angela Avetisyan | VEVA Collect | In Progress | 0.12 | 0.12 |  |  |  | 0 | 0
VC-962 | Story | C/ Project: Create Recording | Angela Avetisyan | VEVA Collect | To Do | 0.58 | 0.33 |  |  |  | 0 | 0
VC-968 | Story | W/ Locked Credits - non ghosted objects | Angela Avetisyan | VEVA Collect | Done | 0.22 | 0.22 | 3 |  |  | 0 | 0
VC-963 | Story | C/ Project: Add Collaborator | Angela Avetisyan | VEVA Collect | To Do | 0.25 | 0.25 |  |  |  | 0 | 0
VC-977 | Story | C/ Project: Generate Check-In code | Angela Avetisyan | VEVA Collect | In Progress | 0.05 | 0.05 |  |  |  | 0 | 0
VC-961 | Story | C/ Project: Create session | Angela Avetisyan | VEVA Collect | To Do | 0.25 | 0.25 |  |  |  | 0 | 0
VC-794 | Story | M/ Leave page with info warning | Angela Avetisyan | VEVA Collect | In Progress | 0.17 | 0.17 |  |  |  | 0 | 0 |  |  | 1
VC-959 | Story | C/ Project: Add credit | Angela Avetisyan | VEVA Collect | To Do | 0.25 | 0.25 |  |  |  | 0 | 0
VC-951 | Story | C/ Songs: Show different number in list. | Angela Avetisyan | VEVA Collect | In Progress | 0.25 | 0.25 |  |  |  | 0 | 0
VC-923 | Bug | M/ Search Parties not always work | Angela Avetisyan | VEVA Collect | Done | 0.17 | 0.17 |  |  |  | 0 | 0
VC-949 | Story | C/ Songs: Expand row | Angela Avetisyan | VEVA Collect | In Progress | 0.05 | 0.05 | 1 |  |  | 0 | 0
VC-881 | Story | W/ Collab. perm. moving files | Angela Avetisyan | VEVA Collect | To Do | 0.33 | 0 | 3 |  |  | 0 | 0 | IN PROGRESS - TO TEST
VC-823 | Story | M/ SoundExchange in Integration section | Angela Avetisyan | VEVA Collect | Done | 0.38 | 0 | 2 |  |  | 0 | 0 |  |  | 1
VC-725 | Story | M/ Projects page: Export RIN 2.0 | Angela Avetisyan | VEVA Collect | In Progress | 0.27 | 0 | 1 |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 1
VC-984 | Story | C/ Project: Add comment to a recording assigned to a session | Angela Avetisyan | VEVA Collect | In Progress | 0.08 | 0.08 |  |  |  | 0 | 0
VC-945 | Story | M/ Share modal with link choice | Angela Avetisyan | VEVA Collect | Done | 0.97 | 0.97 | 2 |  |  | 0 | 0 |  |  | 1
VC-876 | Story | M/ Sub-menu Integrations" MVP" | Angela Avetisyan | VEVA Collect | Done | 0.6 | 0.6 | 2 |  |  | 0 | 0 |  |  | 3
VC-954 | Story | C/ Song: Edit song, fill in all fields and submit | Angela Avetisyan | VEVA Collect | In Progress | 0.08 | 0.08 |  |  |  | 0 | 0
VC-971 | Story | M/ Last Exported dates | Angela Avetisyan | VEVA Collect | Done | 0.08 | 0.08 | 2 |  |  | 0 | 0
VC-880 | Story | W/ Collab. perm. and copy link | Angela Avetisyan | VEVA Collect | To Do | 0.17 | 0.17 | 3 |  |  | 0 | 0
VC-1014 | Story | C/ Account: Integrations-tab, check all go to website | Angela Avetisyan | VEVA Collect | To Do | 0.1 | 0.1 | 2 |  |  | 0 | 0
VC-689 | Story | W/ Create waveform display pane from design | Angela Avetisyan | VEVA Collect | Done | 0.17 | 0.17 | 2 |  |  | 0 | 9.53 | IN PROGRESS - TO TEST |  | 3
VC-974 | Bug | W/ Session dropdown fix | Angela Avetisyan | VEVA Collect | Done | 0.22 | 0.22 | 2 |  |  | 0 | 0
VC-965 | Story | C/ Project: Add/remove from favorites | Angela Avetisyan | VEVA Collect | To Do | 0.08 | 0.08 |  |  |  | 0 | 0
VC-948 | Story | C/ Songs: Search song | Angela Avetisyan | VEVA Collect | In Progress | 0.25 | 0.25 |  |  |  | 0 | 0
VC-1013 | Story | C/ Account: Account-tab, update password | Angela Avetisyan | VEVA Collect | To Do | 0.12 | 0.12 |  |  |  | 0 | 0
VC-995 | Story | W/ Collaborators not allowed to Lock Projects | Angela Avetisyan | VEVA Collect | Done | 0.08 | 0.08 |  |  |  | 0 | 0
VC-973 | Story | W/ Edit F/NF/O fix | Angela Avetisyan | VEVA Collect | Done | 0.08 | 0.08 | 2 |  |  | 0 | 0
VC-969 | Story | W/ Last Exported dates | Angela Avetisyan | VEVA Collect | Done | 0.25 | 0.25 | 1 |  |  | 0 | 0
VC-877 | Story | M/ Lock Credits & Integrations | Angela Avetisyan | VEVA Collect | Done | 0.58 | 0.58 | 3 |  |  | 0 | 0
VC-532 | Story | W/ Recycle Bin: Frontend | Angela Avetisyan | VEVA Collect | In Progress | 1.33 | 1.33 | 2 |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 3
VC-973 | Story | W/ Edit F/NF/O fix | Abdul Jalil | VEVA Collect | Done | 1.57 | 1.57 | 2 |  |  | 0 | 0
VC-974 | Bug | W/ Session dropdown fix | Abdul Jalil | VEVA Collect | Done | 5.12 | 5.12 | 2 |  |  | 0 | 0
VC-995 | Story | W/ Collaborators not allowed to Lock Projects | Abdul Jalil | VEVA Collect | Done | 1.37 | 1.37 |  |  |  | 0 | 0
VC-972 | Bug | W/ Fix positions on integration page | Abdul Jalil | VEVA Collect | Done | 4.05 | 4.05 | 1 |  |  | 0 | 0 |  |  | 1
VC-997 | Story | W/ Modal if owner Locked a Project | Abdul Jalil | VEVA Collect | Done | 1.25 | 1.25 |  |  |  | 0 | 0
VC-705 | Story | W/ Update UI navigation | Abdul Jalil | VEVA Collect | To Do | 44.32 | 44.32 | 3 |  |  | 0 | 0
VC-975 | Bug | W/ Remove Jaxsta from My Party | Abdul Jalil | VEVA Collect | Done | 0.5 | 0.5 | 1 |  |  | 0 | 0
VC-707 | Story | W/ Edit Credit F/NF/O"" | Abdul Jalil | VEVA Collect | Done | 6.05 | 6.05 | 1 |  |  | 0 | 0 | IN PROGRESS - TO QA |  | 2
VC-691 | Story | W/ Create waveform section comment feature | Abdul Jalil | VEVA Collect | To Do | 10.48 | 10.48 | 2 |  |  | 0 | 0
VC-969 | Story | W/ Last Exported dates | Abdul Jalil | VEVA Collect | Done | 2.1 | 2.1 | 1 |  |  | 0 | 0
VC-880 | Story | W/ Collab. perm. and copy link | Abdul Jalil | VEVA Collect | To Do | 0.63 | 0.63 | 3 |  |  | 0 | 0
VC-1010 | Story | W/ Parallel file uploads for better speed | Abdul Jalil | VEVA Collect | Done | 9.75 | 9.75 | 3 |  |  | 0 | 0 | IN PROGRESS - TO TEST
VC-822 | Story | W/ SoundExchange in Integration section | Abdul Jalil | VEVA Collect | Done | 0.53 | 0.53 | 3 |  |  | 0 | 0 | IN PROGRESS - TO QA |  | 2
VC-881 | Story | W/ Collab. perm. moving files | Abdul Jalil | VEVA Collect | To Do | 0.75 | 0.75 | 3 |  |  | 0 | 0 | IN PROGRESS - TO TEST
VC-689 | Story | W/ Create waveform display pane from design | Abdul Jalil | VEVA Collect | Done | 0.5 | 0.5 | 2 |  |  | 0 | 9.53 | IN PROGRESS - TO TEST |  | 3
VC-724 | Story | W/ Projects page: Export RIN 2.0 | Abdul Jalil | VEVA Collect | Done | 3.33 | 3.33 | 2 |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 1
VC-787 | Story | W/ Sub-menu Integrations" MVP" | Abdul Jalil | VEVA Collect | Done | 17.37 | 17.37 | 2 |  |  | 0 | 0 | IN PROGRESS - TO QA |  | 1
VC-968 | Story | W/ Locked Credits - non ghosted objects | Abdul Jalil | VEVA Collect | Done | 14.63 | 14.63 | 3 |  |  | 0 | 0
VC-692 | Story | W/ Create waveform view comment feature | Abdul Jalil | VEVA Collect | In Progress | 5.27 | 5.27 | 2 |  |  | 0 | 0
VC-875 | Story | W/ Lock Credits & Integrations | Abdul Jalil | VEVA Collect | Done | 13.67 | 13.67 | 4 |  |  | 0 | 0 | IN PROGRESS - TO QA
VC-532 | Story | W/ Recycle Bin: Frontend | Abdul Jalil | VEVA Collect | In Progress | 11.23 | 11.23 | 2 |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 3
VC-994 | Story | S/ Sample Project should never be exported | Mohsin | VEVA Collect | Done | 8.5 | 8.5 |  |  |  | 0 | 0 |  |  | 1
VC-845 | Bug | S/ Share empty folders modal text | Mohsin | VEVA Collect | In Progress | 4 | 4 | 1 |  |  | 0 | 0 |  |  | 1
VC-826 | Story | S/ Install Mixpanel on server | Mohsin | VEVA Collect | To Do | 4 | 4 | 2 |  |  | 0 | 0
VC-970 | Story | S/ Last Exported dates | Mohsin | VEVA Collect | Done | 9 | 9 |  |  |  | 0 | 0 |  |  | 1
VC-813 | Story | S/ SoundExchange backend integration | Mohsin | VEVA Collect | Done | 5 | 5 | 8 |  |  | 0 | 0 | IN PROGRESS - TO TEST
VC-1018 | Task | S/ RESEARCH: watermarking of audio files | Mohsin | VEVA Collect | To Do | 9 | 9 | 2 |  |  | 0 | 0
VC-792 | Story | S/ Notification if 2FA is inactivated. | Mohsin | VEVA Collect | In Progress | 4 | 4 | 1 |  |  | 0 | 0
VC-723 | Story | S/ Export RIN 2.0 API support | Mohsin | VEVA Collect | Done | 36 | 36 | 3 |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 3
VC-855 | Story | S/ Discount code feedback to user | Mohsin | VEVA Collect | In Progress | 3.5 | 3.5 | 1 |  |  | 0 | 0
VC-673 | Story | S/ Account referal: backend | Mohsin | VEVA Collect | In Progress | 24 | 24 | 8 |  |  | 0 | 0
VC-531 | Story | W/ Recycle Bin: Backend | Mohsin | VEVA Collect | In Progress | 2.5 | 2.5 |  |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 1
VC-1012 | Story | C/ Account: Account-tab, change timezone | Samvel Sadoyan | VEVA Collect | In Progress | 1.22 | 1.22 | 1 |  |  | 0 | 0
VC-1011 | Story | C/ Account: Account-tab, change account info | Samvel Sadoyan | VEVA Collect | In Progress | 1 | 1 | 1 |  |  | 0 | 0
VC-908 | Story | C/ Party: ISNI link | Samvel Sadoyan | VEVA Collect | In Progress | 1 | 1 | 2 |  |  | 0 | 0
VC-986 | Story | C/ Project: View a recording in a session | Samvel Sadoyan | VEVA Collect | In Progress | 1 | 1 | 1 |  |  | 0 | 0
VC-981 | Story | C/ Project: Edit credit for session | Samvel Sadoyan | VEVA Collect | In Progress | 7.17 | 7.17 | 3 |  |  | 0 | 0
VC-978 | Story | C/ Project: Edit session details | Samvel Sadoyan | VEVA Collect | In Progress | 4 | 4 | 3 |  |  | 0 | 0
VC-980 | Story | C/ Project: Add credit to session | Samvel Sadoyan | VEVA Collect | In Progress | 3.83 | 3.83 | 4 |  |  | 0 | 0
VC-1015 | Story | C/ Account: Integrations-tab, check all about integration | Samvel Sadoyan | VEVA Collect | In Progress | 0.83 | 0.83 | 3 |  |  | 0 | 0
VC-809 | Story | C/ Favorites: toggle favorites | Samvel Sadoyan | VEVA Collect | In Progress | 0.98 | 0.98 | 1 |  |  | 0 | 0
VC-977 | Story | C/ Project: Generate Check-In code | Samvel Sadoyan | VEVA Collect | In Progress | 1.67 | 1.67 | 1 |  |  | 0 | 0
VC-1014 | Story | C/ Account: Integrations-tab, check all go to website | Samvel Sadoyan | VEVA Collect | To Do | 9.22 | 9.22 | 2 |  |  | 0 | 0
VC-985 | Story | C/ Project: Remove a recording from a session | Samvel Sadoyan | VEVA Collect | In Progress | 1.17 | 1.17 | 1 |  |  | 0 | 0
VC-952 | Story | C/ Songs: Change page in list | Samvel Sadoyan | VEVA Collect | In Progress | 0.75 | 0.75 | 1 |  |  | 0 | 0
VC-953 | Story | C/ Song: Click to enter song details page | Samvel Sadoyan | VEVA Collect | In Progress | 0.35 | 0.35 | 1 |  |  | 0 | 0
VC-956 | Story | C/ Song: Search file | Samvel Sadoyan | VEVA Collect | In Progress | 0.28 | 0.28 | 1 |  |  | 0 | 0.08
VC-770 | Story | C/ Add Party | Samvel Sadoyan | VEVA Collect | In Progress | 0.17 | 0.17 | 2 |  |  | 0 | 0
VC-954 | Story | C/ Song: Edit song, fill in all fields and submit | Samvel Sadoyan | VEVA Collect | In Progress | 0.28 | 0.28 | 1 |  |  | 0 | 0
VC-951 | Story | C/ Songs: Show different number in list. | Samvel Sadoyan | VEVA Collect | In Progress | 0.5 | 0.5 | 3 |  |  | 0 | 0
VC-984 | Story | C/ Project: Add comment to a recording assigned to a session | Samvel Sadoyan | VEVA Collect | In Progress | 1 | 1 | 2 |  |  | 0 | 0
VC-948 | Story | C/ Songs: Search song | Samvel Sadoyan | VEVA Collect | In Progress | 1.5 | 1.5 | 3 |  |  | 0 | 0
VC-949 | Story | C/ Songs: Expand row | Samvel Sadoyan | VEVA Collect | In Progress | 1 | 1 | 1 |  |  | 0 | 0
VC-909 | Story | C/ Party: Edit a Party | Samvel Sadoyan | VEVA Collect | In Progress | 0.5 | 0.5 |  |  |  | 0 | 0
VC-983 | Story | C/ Project: Expand credit row on session credit | Samvel Sadoyan | VEVA Collect | In Progress | 2.08 | 2.08 |  |  |  | 0 | 0
VC-979 | Story | C/ Project: Assign recording to session | Samvel Sadoyan | VEVA Collect | In Progress | 1 | 1 |  |  |  | 0 | 0
VC-971 | Story | M/ Last Exported dates | Narek Poghosyan | VEVA Collect | Done | 1 | 1 | 2 |  |  | 0 | 0
VC-833 | Story | M/ Type date manually | Narek Poghosyan | VEVA Collect | To Do | 2 | 2 | 2 |  |  | 0 | 0
VC-883 | Story | M/ Collab. perm. and copy link | Narek Poghosyan | VEVA Collect | To Do | 3 | 3 | 3 |  |  | 0 | 0
VC-681 | Story | M/ Set social icons | Narek Poghosyan | VEVA Collect | To Do | 1 | 1 | 2 |  |  | 0 | 0
VC-876 | Story | M/ Sub-menu Integrations" MVP" | Narek Poghosyan | VEVA Collect | Done | 10.17 | 10.17 | 2 |  |  | 0 | 0 |  |  | 3
VC-877 | Story | M/ Lock Credits & Integrations | Narek Poghosyan | VEVA Collect | Done | 19.33 | 19.33 | 3 |  |  | 0 | 0
VC-683 | Story | M/ Show social icons | Narek Poghosyan | VEVA Collect | In Progress | 0.5 | 0.5 | 2 |  |  | 0 | 0
VC-823 | Story | M/ SoundExchange in Integration section | Narek Poghosyan | VEVA Collect | Done | 0.5 | 0.5 | 2 |  |  | 0 | 0 |  |  | 1
VC-1005 | Story | M/ F/NF/O logic | Narek Poghosyan | VEVA Collect | To Do | 9.17 | 9.17 | 3 |  |  | 0 | 0
VC-945 | Story | M/ Share modal with link choice | Narek Poghosyan | VEVA Collect | Done | 11.33 | 11.33 | 2 |  |  | 0 | 0 |  |  | 1
VC-715 | Story | M/ Edit Credit F/NF/O"" | Narek Poghosyan | VEVA Collect | Done | 5.67 | 5.67 | 2 |  |  | 0 | 0 |  |  | 2
VC-725 | Story | M/ Projects page: Export RIN 2.0 | Narek Poghosyan | VEVA Collect | In Progress | 4.67 | 4.67 | 1 |  |  | 0 | 0 | IN PROGRESS - TO TEST |  | 1